## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 1
PROJECT NAME | Organisational Information sharing and Leave Management System
PROJECT MENTOR (sponsor) | Shahid Ahmed (Eklavya Foundation)
TEAM MEMBERS | Ananthula Sai Ravichandra
Krishiv Gupta
Chaitanya Thogata
Aditya Chandramouli
Sai Aditya

## Status
PROJECT NUMBER | 1
PROJECT NAME | Organisational Information sharing and Leave Management System
PROJECT MENTOR (sponsor) | Shahid Ahmed (Eklavya Foundation)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 20- January 27)
Fix meeting with client | Coordination | Ravi | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Chandramouli | 0.5 | 0.2 | Done |  | 0.3 | 150
Client meeting | Coordination | All | 1 | 1 | Done | Meeting happened on 25th Jan | 0 | 0
MoM creation | Documentation | Chaitanya | 1 | 1 | Done | Resolved some ambiguity on the product structure and clarified requirements | 0 | 0
Project Plan writeup | Documentation | Ravi | 1 | 1 | Done |  | 0 | 0
Week 2 (January 27 - February 3)
Week 3 (January 29 - February 4)
Week 4
Week 5
Week 6